## Aggr CIP
2020-2026 CAPITAL IMPROVEMENT PLAN AGGREGATE WORKSHEET
|  | TOTAL |  | TOTAL | FUTURE | FYE2021 |  | FYE2022 |  | FYE2023 |  | FYE2024 |  | FYE2025 |  | FYE2026 |  | FYE2027
| POTENTIAL | PROJECT | TOWNSHIP | TOWNSHIP | COST | PROJECT | CITY | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP
PROJECT NUMBER AND NAME | FUNDING SOURCE(S) | COST | SHARE | COST | (2020-2026) | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST
Water Improvements | W & S Retained Earnings or Bond Sale | 17650000 | 100% | 14715000 | 13995000 | 4000000 | 4000000 | 5870000 | 2935000 | 3610000 | 3610000 | 3450000 | 3450000 | 720000 | 720000 | 0 | 0 | 0 | 0
Sub-Total |  | 17650000 |  | 14715000 | 13995000 | 4000000 | 4000000 | 5870000 | 2935000 | 3610000 | 3610000 | 3450000 | 3450000 | 720000 | 720000 | 0 | 0 | 0 | 0
Fire Fund
#REF! | Fire Fund | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Sub-Total |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Parks
Park Development | Township, Grants, Donations | 238000 | 75% | 178500 | 178500 | 0 | 0 | 62500 | 46875 | 78000 | 58500 | 53500 | 40125 | 44000 | 33000 | 0 | 0 | 0 | 0
Total |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Charts
2020-2026 Capital Improvement Plan
Water Improvements | 14715000 | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
Parks | 178500 | #REF!
Total | #REF!

## Water
2020-2026 CAPITAL IMPROVEMENT PLAN
[6 empty] | TOTAL |  | TOTAL | FUTURE | FYE2021 |  | FYE2022 |  | FYE2023 |  | FYE2024 |  | FYE2025 |  | FYE2026 |  | FYE2027
|  | PROJECT | PROJECT | AVERAGE | POTENTIAL | PROJECT | TOWNSHIP | TOWNSHIP | COST | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP
| PROJECT NUMBER AND NAME | COORDINATION | TYPE | RATING | FUNDING SOURCE(S) | COST | SHARE | COST | (2020-2026) | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST
Water System Improvements
WM-1 | Water Main Replacement | None | Rehabilitation |  | W & S Retained Earnings or Bond Sale | 4000000 | 100% | 4000000 | 4000000 | 4000000 | 4000000
WM-2 | Liberty Road 16” Water Main (1) | ? | New |  | Water Fund & Developer | 5870000 | 50% | 2935000 | 2935000 |  |  | 5870000 | 2935000
WT-1 | Wagner Road 0.5 MG Water Tower (1) | ? | New |  | Water Fund | 3610000 | 100% | 3610000 | 3610000 |  |  |  |  | 3610000 | 3610000
WM-3 | Baker Road/Staebler Road Loop (1) | ? | New |  | Water Fund | 3450000 | 100% | 3450000 | 3450000 | [6 empty] | 3450000 | 3450000
WM-4 | I-94/Zeeb Road Second Crossing (1) | ? | New |  | Water Fund/Developer? | 720000 | 100% | 720000 | [9 empty] | 720000 | 720000
| Sub-Total |  |  |  |  | 17650000 |  | 14715000 | 13995000 | 4000000 | 4000000 | 5870000 | 2935000 | 3610000 | 3610000 | 3450000 | 3450000 | 720000 | 720000 | 0 | 0 | 0 | 0
(1) Based on March, 2014 Water Study

## Sewer
2020-2026 CAPITAL IMPROVEMENT PLAN
[5 empty] | TOTAL |  | TOTAL | FUTURE | FYE2021 |  | FYE2022 |  | FYE2023 |  | FYE2024 |  | FYE2025 |  | FYE2026 |  | FYE2027
| PROJECT | PROJECT | AVERAGE | POTENTIAL | PROJECT | TOWNSHIP | TOWNSHIP | COST | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP
PROJECT NUMBER AND NAME | COORDINATION | TYPE | RATING | FUNDING SOURCE(S) | COST | SHARE | COST | (2020-2026) | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST
Sub-Total

## Fire
2020-2027 CAPITAL IMPROVEMENT PLAN AGGREGATE SPREADSHEET
[6 empty] | TOTAL |  | TOTAL | FUTURE | FYE2021 |  | FYE2022 |  | FYE2023 |  | FYE2024 |  | FYE2025 |  | FYE2026 |  | FYE2027 |  | FYE2028
|  | PROJECT | PROJECT | AVERAGE | POTENTIAL | PROJECT | TOWNSHIP | TOWNSHIP | COST | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP
| PROJECT NUMBER AND NAME | COORDINATION | TYPE | RATING | FUNDING SOURCE(S) | COST | SHARE | COST | (2020-2026) | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST
Fire Equipment
FE-1 | Staff vehicle, EMS vehicle | None | Replacement |  | Fire Fund | 75000 | 100% | 75000 | 90000 | 35000 | 35000 | 55000 | 55000
FE-2 | Brush Truck, Tanker | None | Replacement |  | Fire Fund | 573000 | 100% | 573000 | 573000 |  |  |  |  | 573000 | 573000
| Engine, tanker |  | New |  | Undetermined |  |  |  | 0
| Staff vehicle-inspector |  | New |  | Fire Fund |  |  |  | 55000 |  |  |  |  | 55000 | 55000
| Ladder truck and tanker | [14 empty] | 1875000 | 1875000
| Sub-Total |  |  |  |  | 648000 |  | 648000 | 718000 | 35000 | 35000 | 55000 | 55000 | 628000 | 628000 | 1875000 | 1875000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Fire Facilities | [7 empty] | 0
FF-1 | Station #1 Phase 2 Improvements |  |  |  | Loan from general fund | 1500000 | 100% | 1500000 | 1500000 |  |  | 1500000 | 1500000
| Property acquisition |  |  |  | Undetermined |  |  |  | 900000 |  |  |  |  | 150000 | 150000 | [6 empty] | 750000 | 750000
| Construction of fire station |  |  |  | Undetermined |  |  |  | 4000000 | [6 empty] | 4000000 | 4000000
.
| Sub-Total |  |  |  |  | 1500000 |  | 1500000 | 6400000 | 0 | 0 | 1500000 | 1500000 | 150000 | 150000 | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 0
| Total |  |  |  |  | 2148000 |  | 2148000 | 7118000 | 35000 | 35000 | 1555000 | 1555000 | 778000 | 778000 | 5875000 | 5875000 | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 0
Phase two improvements can be completed within the current budget, borrowing the funds from the General Fund and repaying them. The general fund can sustain a loan for this project per analysis by CFO Egeler and myself. Proposed payback
includes current and ongoing budget line item of $70,000 (line item 206.000.975). Per our evaluation, we could afford a payback at $75,000 annually, with additional amounts based on year end budget experience. Payback should be 12-15 years.
Near term, we need to look at creating a fire inspector position. The only capital costs associated with this would be a vehicle
Long term, we have the need to additional buildings to adequately service the community. With property acquired in the SE area of the Township, the next major area off need is the west side of the Township along Jackson Ave
This CIP considers a second station operating by the end of FYE 2025. This station was projected to be open and operating in 2020.
If Dexter were no longer to staff their downtown fire station, this may need to be ammended.

## Parks
2020-2026 CAPITAL IMPROVEMENT PLAN
[6 empty] | TOTAL |  | TOTAL | FUTURE | FYE2021 |  | FYE2022 |  | FYE2023 |  | FYE2024 |  | FYE2025 |  | FYE2026 |  | FYE2027
|  | PROJECT | PROJECT | AVERAGE | POTENTIAL | PROJECT | TOWNSHIP | TOWNSHIP | COST | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP
| PROJECT NUMBER AND NAME | COORDINATION | TYPE | RATING | FUNDING SOURCE(S) | COST | SHARE | COST | (2020-2026) | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST
Park Development
PD-1 | Develop Marshall Park | None | New |  | Township, Grants, Donations | 27000 | 75% | 20250 | 20250 |  |  | 15000 | 11250 | 11000 | 8250 | 1000 | 750
PD-1 | Develop West Scio Preserve | None | New |  | Township, Grants, Donations | 14000 | 75% | 10500 | 10500 |  |  | 14000 | 10500
PD-1 | Develop Wild Preserve | None | New |  | Township, Grants, Donations | 27000 | 75% | 20250 | 20250 |  |  | 13500 | 10125 | 11000 | 8250 | 2500 | 1875
PD-1 | Develop Township Hall Park | None | New |  | Township, Grants, Donations | 51000 | 75% | 38250 | 38250 |  |  | 20000 | 15000 | 22000 | 16500 | 9000 | 6750
PD-1 | Develop Sloan Preserve | None | New |  | Township, Grants, Donations | 61000 | 75% | 45750 | 45750 |  |  |  |  | 12000 | 9000 | 5000 | 3750 | 44000 | 33000
PD-1 | Develop Van Curler Preserve | None | New |  | Township, Grants, Donations | 58000 | 75% | 43500 | 43500 |  |  |  |  | 22000 | 16500 | 36000 | 27000
0
| Total |  |  |  |  | 238000 |  | 178500 | 178500 | 0 | 0 | 62500 | 46875 | 78000 | 58500 | 53500 | 40125 | 44000 | 33000 | 0 | 0 | 0 | 0
0

## Pathways
2020-2026 CAPITAL IMPROVEMENT PLAN
[5 empty] | TOTAL |  | TOTAL | FUTURE | FYE2021 |  | FYE2022 |  | FYE2023 |  | FYE2024 |  | FYE2025 |  | FYE2026 |  | FYE2027
| PROJECT | PROJECT | AVERAGE | POTENTIAL | PROJECT | TOWNSHIP | TOWNSHIP | COST | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP
PROJECT NUMBER AND NAME | COORDINATION | TYPE | RATING | FUNDING SOURCE(S) | COST | SHARE | COST | (2020-2026) | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST
Total

## Preservation
2020-2026 CAPITAL IMPROVEMENT PLAN
[5 empty] | TOTAL |  | TOTAL | FUTURE | FYE2021 |  | FYE2022 |  | FYE2023 |  | FYE2024 |  | FYE2025 |  | FYE2026 |  | FYE2027
| PROJECT | PROJECT | AVERAGE | POTENTIAL | PROJECT | TOWNSHIP | TOWNSHIP | COST | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP | PROJECT | TOWNSHIP
PROJECT NUMBER AND NAME | COORDINATION | TYPE | RATING | FUNDING SOURCE(S) | COST | SHARE | COST | (2020-2026) | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST | COST
Total